## UNITEL
Project UNI-TEL /Modernisation and internationalisation of Iranian Universities through collaborative TEL-based curriculum development in engineering and STEM Programme: Erasmus+ ¦ Key Action 2 ¦ Capacity Building in Higher Education
CODE | PREPARATION |  | 1st YEAR | [11 empty] | 2nd YEAR | [11 empty] | 3rd YEAR
|  | Total No of weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | Baseline analysis -
Constitution of Research and Educational Team | bar: 1st YEAR 1
1.1 | Analysis and synthesis of data - State of the Art of HEIs in Engineering and STEM studies (Institutional level) (pedagogical approaches and ICT-supported tools and systems) | bar: 1st YEAR 1 to 1st YEAR 4
1.2 | Analysis and synthesis of data - State of the Art of HEIs in Engineering and STEM studies (National level) (pedagogical approaches and ICT-supported tools and systems) | bar: 1st YEAR 4 to 1st YEAR 5
1.3 | Analysis and synthesis of data - State of the Art of HEIs in Engineering and STEM studies at EU level (pedagogical approaches and ICT-supported tools and systems) | bar: 1st YEAR 5 to 1st YEAR 6
1.4 | Addendum for Skills and competences of the Universities’ lecturers in line with the digital education era | bar: 1st YEAR 4 to 1st YEAR 6
1.5 | Comparative analysis of state of the art in PC and EU for harmonisation of currculum development purposes | bar: 1st YEAR 6 to 1st YEAR 7
1.6 | Preparation of Guidelines with recommendations about current practices in partner countries for curricula modernization | bar: 1st YEAR 7 to 1st YEAR 8
1.7 | Roadmap on industry-relevant Skills and competences | bar: 1st YEAR 6 to 1st YEAR 7
Dev.
1 | Comparative analysis (State of the Art of HEIs in Engineering and STEM studies) | bar: 1st YEAR 6
2 | Guidelines for modernising HEIs engineering and STEM studies curriculum integrating new pedagogical and digital learning approaches | bar: 1st YEAR 8
3 | Roadmap on industry-relevant Skills and competences | bar: 1st YEAR 7
CODE | DEVELOPMENT | Total No of weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP2 | UNI-TEL training path development - Work package leader P3 (UTU - FI)
Building the Pedagogical development team. | bar: 8
2.1 | Development of educational concept for the UNI-TEL training path. | bar: 8 to 10
2.2 | Development of the virtual environment prototype | bar: 9 to 11
2.3 | Development of UNI-TEL technological infrastructure in each PC University involved in the project | bar: 10 to 13
2.4 | Development of the UNI-TEL e-course: 36 h (12 weeks) | bar: 10 to 14
2.5 | Publishing the UNI-TEL e-course on the Project platform & internal tests | bar: 14
Dev.
4 | UNI-TEL training path | bar: 10
5 | UNI-TEL e-course | bar: 14
6 | UNI-TEL virtual environment | bar: 14
CODE | DEVELOPMENT |  | 1: 1st YEAR; 13: 2nd YEAR; 25: 3rd YEAR
|  | Total No of weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP3 | UNI-TEL training delivery
3.1 | Selection of participating professors and instructional designers | bar: 2nd YEAR 13 to 2nd YEAR 14
3.2 | Training of national tutors (in presence) - study visits | bar: 1st YEAR 10; 2nd YEAR 14
3.3 | Delivery of the e-course for professors and instructional designers | bar: 2nd YEAR 15 to 2nd YEAR 18
3.4 | Delivery of in presence sessions of the training (one per months total 4)
3.5 | Evaluation of the course delivery | bar: 2nd YEAR 18
3.6 | Tranining delivery report | bar: 2nd YEAR 18
Dev.
7 | UNI-TEL training delivery report | bar: 2nd YEAR 19
CODE | DEVELOPMENT |  | 1st YEAR 1: 1st YEAR; 2nd YEAR 13: 2nd YEAR; 3rd YEAR 25: 3rd YEAR
|  | Total No of weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP4 | UNI-TEL curriculum modernisation - Work package leader P1 (USGM - IT)
Building the Experimentation team. | bar: 2nd YEAR 18
4.1 | Trained lecturers modernise their curricula through integration of ICT-based approaches and contents. | bar: 2nd YEAR 19 to 2nd YEAR 24
The modernised curricula are published on the University e-paltforms and tested from the technical point of view | bar: 2nd YEAR 23 to 2nd YEAR 24
4.2 | Trained lecturers develop at least 1 remote lab | bar: 2nd YEAR 19 to 2nd YEAR 24
4.3 | Approval and accreditation of the modernised curricula by the authorised University Bodies. | bar: 2nd YEAR 24 to 3rd YEAR 25
4.4 | Piloting of the modernised curricula with a testing groups of students. | bar: 2nd YEAR 24 to 3rd YEAR 36
Dev.
8 | Modernised curricula | bar: 2nd YEAR 24
9 | Modernised curricula - piloting report | bar: 3rd YEAR 34
CODE | QUALITY PLAN |  | 1st YEAR 1: 1st YEAR; 2nd YEAR 13: 2nd YEAR; 3rd YEAR 25: 3rd YEAR
|  | Total No of weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP5 | QUALITY ASSURANCE AND EVALUATION; Package Leader P4 (UAb –PT)
Setting up of the Quality and Evaluation Team. | bar: 1st YEAR 1 to 1st YEAR 2
5.1 | Drawing up of the Quality and Evaluation Plan. | bar: 1st YEAR 1 to 1st YEAR 2
5.2 | External Quality Expert selection | bar: 1st YEAR 2
5.3 | Design and submission of “expectations and satisfactions” questionnaires for lecturers | bar: 1st YEAR 2; 2nd YEAR 15; 2nd YEAR 18
Design and submission of template for the self-evaluation report to the lecturers | bar: 1st YEAR 2; 2nd YEAR 23
Design and submission of “expectations and satisfactions” questionnaires for students. | bar: 3rd YEAR 25; 3rd YEAR 33
5.4 | Processing data and analysis at national and international level.
Drawing up of the Quality Reports for the management and the products.
Drawing up of the Final Evaluation Report | bar: 3rd YEAR 35 to 3rd YEAR 36
Dev.
10 | Evaluation plan | bar: 1st YEAR 2
11 | Quality report for the project management | bar: 1st YEAR 11; 2nd YEAR 24; 3rd YEAR 34
12 | Quality report for the products | bar: 2nd YEAR 15; 3rd YEAR 33
13 | Final Evaluation Report | bar: 3rd YEAR 36
CODE | DISSEMINATION AND EXPLOITATION |  | 1st YEAR 1: 1st YEAR; 2nd YEAR 13: 2nd YEAR; 3rd YEAR 25: 3rd YEAR
|  | Total No of weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP6 | DISSEMINATION AND EXPLOITATION - Shiraz
Valorisation team setting up | bar: 1st YEAR 1 to 1st YEAR 2
6.1 | Valorisation plan drawing up | bar: 1st YEAR 1 to 1st YEAR 2
6.2 | Poster/brochures design and printing | bar: 1st YEAR 3; 2nd YEAR 24; 3rd YEAR 35
Poster/brochures distribution
6.3 | Participation in key thematic conference on national/international level Papers drawing up
6.4 | UNI-TEL website design & updating
6.5 | Drawing up and distribution of e-Newsletters | bar: 1st YEAR 2; 1st YEAR 9; 1st YEAR 12; 2nd YEAR 16; 2nd YEAR 21; 2nd YEAR 24; 3rd YEAR 27; 3rd YEAR 32; 3rd YEAR 36
6.6 | Identification of national key stakeholders | bar: 1st YEAR 2 to 2nd YEAR 24; 3rd YEAR 32 to 3rd YEAR 33
Delivery of promotional materials to the key actors at national level | bar: 1st YEAR 3 to 2nd YEAR 24; 3rd YEAR 36
6.7 | Organisation of 1st national exploitation event | bar: 2nd YEAR 15
Organisation of 2nd national exploitation event | bar: 3rd YEAR 30 to 3rd YEAR 36
6.8 | Exploitation Agreement definition | bar: 3rd YEAR 36
Dev.
14 | Valorisation plan | bar: 1st YEAR 2
15 | UNI-TEL Website | bar: 1st YEAR 2
16 | Paper products(brochure (B), poster (Po), papers) |  | 1st YEAR 3: B Po; 2nd YEAR 24: B; 3rd YEAR 35: B
17 | E-newsletter (3 per year) | bar: 1st YEAR 2; 1st YEAR 9; 1st YEAR 12; 2nd YEAR 16; 2nd YEAR 21; 2nd YEAR 24; 3rd YEAR 27; 3rd YEAR 32; 3rd YEAR 36
18 | Final International Conference | bar: 3rd YEAR 36
19 | First national exploitation event | bar: 2nd YEAR 13
20 | Second national exploitation event | bar: 2nd YEAR 24
21 | Exploitation Agreement | bar: 3rd YEAR 36
CODE | MANAGEMENT |  | 1st YEAR 1: 1st YEAR; 2nd YEAR 13: 2nd YEAR; 3rd YEAR 25: 3rd YEAR
|  | Total No of weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP7 | DPROJECT MANAGEMENT; Package Leader P1 USGM - IT)
7,1 | Signing of the contracts | bar: 1st YEAR 1 to 1st YEAR 2
7,2 | Constitution of Steering Committee and work teams | bar: 1st YEAR 1 to 1st YEAR 2
7,3 | Drawing up the UNI-TEL management handbook and work plan | bar: 1st YEAR 1 to 1st YEAR 2
7,4 | Management of project activities and administrative issues
Communication among the partners, with EACEA agency, etc.
7.5 | Participation at the EACEA meetings | bar: 1st YEAR 1; 2nd YEAR 13; 3rd YEAR 25
7.6 | Setting up and participation in the project meetings (plenary and virtual) | bar: 1st YEAR 2; 1st YEAR 5; 1st YEAR 8; 1st YEAR 12 to 2nd YEAR 13; 2nd YEAR 17; 2nd YEAR 20; 2nd YEAR 24; 3rd YEAR 26; 3rd YEAR 29; 3rd YEAR 33; 3rd YEAR 36
Formulation of monitoring tools | bar: 1st YEAR 1 to 1st YEAR 3
Collecting the project monitoring activities data (with continuous updating of the project work plan shared with partners)
Drawing up the progress and final reports | bar: 1st YEAR 11 to 1st YEAR 12; 2nd YEAR 23 to 2nd YEAR 24; 3rd YEAR 35 to 3rd YEAR 36
Dev.
22 | UNI-TEL Project Handbook | bar: 1st YEAR 2
23 | Meeting reports (P - p=plenary and V - v=virtual) |  | 1st YEAR 2: p; 1st YEAR 5: v; 1st YEAR 7: p; 1st YEAR 9: Tutors; 1st YEAR 12: v; 2nd YEAR 13: p; 2nd YEAR 14: Tutors; 2nd YEAR 17: v; 2nd YEAR 18: P; 2nd YEAR 22: V; 2nd YEAR 24: P; 3rd YEAR 27: V; 3rd YEAR 28: P; 3rd YEAR 33: v; 3rd YEAR 35: p
Meetings:
1st: Rome (USGM)
2nd: Turku (UTU)
3rd: Isfahan
Tutors: Rome
4th: Qazvin (IKIU)
5th: Ahvaz
6th: Shiraz (SU)
7th Final meeting and conference: Tehran (TU)

## Partner
CBHE - 2019
| Partner ID | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Country code
|  | USGM (IT) | UTU (FI) | Uab (PT) | PRISMA (GR) | IKIU (IR) | USB (IR) | SU (IR | IUT (IR) | TU (IR) | SCU (IR) | SUT (IR) | Namvaran (IR)
CODE | PRE | P1: PARTNER LEADER: P9 TU (IR) and P2 UTU (FI)
WP1 | Baseline analysis - Tehran
Constitution of Research and Educational Team
1.1 | Analysis and synthesis of data - State of the Art of HEIs in Engineering and STEM studies (Institutional level) (pedagogical approaches and ICT-supported tools and systems) | bar: P2; P5 to P11
1.2 | Analysis and synthesis of data - State of the Art of HEIs in Engineering and STEM studies (National level) (pedagogical approaches and ICT-supported tools and systems) | bar: P1 to P2; P11
1.3 | Analysis and synthesis of data - State of the Art of HEIs in Engineering and STEM studies at EU level (pedagogical approaches and ICT-supported tools and systems) | bar: P1 to P3; P11
1.4 | Addendum for Skills and competences of the Universities’ lecturers in line with the digital education era | bar: P2; P11
1.5 | Comparative analysis of state of the art in PC and EU for harmonisation of currculum development purposes | bar: P1 to P2; P11
1.6 | Preparation of Guidelines with recommendations about current practices in partner countries for curricula modernization | bar: P1 to P2; P11 to P12
1.7 | Roadmap on industry-relevant Skills and competences | bar: P1 to P2; P4; P11 to P12
CODE | DEV | P1: PARTNER LEADER: P3 UTU (FI) and P10 SUT (IR)
WP2 | UNI-TEL training path development - Work package leader P3 (UTU - FI) | bar: P2; P11
Building the Pedagogical development team.
2.1 | Development of educational concept for the UNI-TEL training path. | bar: P1 to P2; P11
2.2 | Development of the virtual environment prototype | bar: P1 to P2; P4; P11
2.3 | Development of UNI-TEL technological infrastructure in each PC University involved in the project | bar: P1 to P2; P4; P11
2.4 | Development of the UNI-TEL e-course: 36 h (12 weeks)
2.5 | Publishing the UNI-TEL e-course on the Project platform & internal tests | bar: P1 to P2; P4; P11
CODE | DEV | P1: PARTNER LEADER: P4 and P6 USB (IR)
WP3 | UNI-TEL training delivery - Tedesco | bar: P4; P6
3.1 | Selection of participating professors and instructional designers | bar: P4 to P11
3.2 | Training of national tutors (in presence) | bar: P1 to P2; P4 to P11
3.3 | Delivery of the e-course for professors and instructional designers | bar: P4 to P11
3.4 | Delivery of in presence sessions of the training | bar: P1 to P2; P4 to P11
3.5 | Evaluation of the course delivery | bar: P4; P6
3.6 | Tranining delivery report | bar: P4; P6
CODE | DEV | P1: PARTNER LEADER: P1 USGM (IT) and P5 IKIU (IR)
WP4 | UNI-TEL curriculum modernisation - Work package leader P1 (USGM - IT) | bar: P9
Building the Experimentation team.
4.1 | Trained lecturers modernise their curricula through integration of ICT-based approaches and contents.
The modernised curricula are published on the University e-paltforms and tested from the technical point of view | bar: P5 to P11
4.2 | Trained lecturers develop at least 1 remote lab | bar: P5 to P11
4.3 | Approval and accreditation of the modernised curricula by the authorised University Bodies. | bar: P5 to P11
4.4 | Piloting of the modernised curricula with a testing groups of students. | bar: P5 to P11
CODE | QA | P1: PARTNER LEADER:P3 UAb (PT) and P8 Uok (IR)
WP5 | QUALITY ASSURANCE AND EVALUATION; Package Leader P4 (UAb –PT) | bar: P3; P10
Setting up of the Quality and Evaluation Team.
5.1 | Drawing up of the Quality and Evaluation Plan. | bar: P3; P10
5.2 | External Quality Expert selection | bar: P3; P10
5.3 | Design and submission of “expectations and satisfactions” questionnaires for lecturers | bar: P3; P5 to P12
Design and submission of template for the self-evaluation report to the lecturers | bar: P3; P5 to P12
Design and submission of “expectations and satisfactions” questionnaires for students. | bar: P3; P5 to P11
5.4 | Processing data and analysis at national and international level. | bar: P3; P10
Drawing up of the Quality Reports for the management and the products. | bar: P3; P10
Drawing up of the Final Evaluation Report | bar: P3; P10
CODE | DIS | P1: PARTNER LEADER: P7 SU (IR) and P1 USGM (IR)
WP6 | DISSEMINATION AND EXPLOITATION | bar: P7
Valorisation team setting up
6.1 | Valorisation plan drawing up | bar: P7
6.2 | Poster/brochures design and printing | bar: P7
Poster/brochures distribution
6.3 | Papers drawing up | bar: P7 to P11
6.4 | UNI-TEL website design & updating | bar: P7
6.5 | Drawing up and distribution of e-Newsletters | bar: P7
Participation in key thematic conference on national/international level | bar: P5 to P11
6.6 | Identification of national key stakeholders | bar: P5 to P12
Delivery of promotional materials to the key actors at national level | bar: P5 to P11
6.7 | Organisation of 1st national exploitation event | bar: P5 to P11
Organisation of 2nd national exploitation event | bar: P5; P7
6.8 | Exploitation Agreement definition
CODE | MAN | P1: PARTNER LEADER: P1 USGM (IT)
WP7 | PROJECT MANAGEMENT; Package Leader P1 USGM - IT)
7,1 | Signing of the contracts
7,2 | Constitution of Steering Committee and work teams
7,3 | Drawing up the UNI-TEL management handbook and work plan | bar: P9
7,4 | Management of project activities and administrative issues | bar: P9
Communication among the partners, with EACEA agency, etc.
7.5 | Participation at the EACEA meetings | bar: P9
7.6 | Setting up and participation in the project meetings (plenary and virtual)
Formulation of monitoring tools | bar: P9
Collecting the project monitoring activities data (with continuous updating of the project work plan shared with partners)
Drawing up the progress and final reports
Active Involvement
Participation
Co-leadership